## CAREpoint3 Plan
{Customer Name} CAREpoint Implementation Project Plan
|  |  | CAREpoint Target Go-Live: |  | {Date}
|  |  | e-Bridge {version} Go-Live |  | {Date}
|  |  | Estimated Project Completion: |  | {Date}
Customer Name:
Item | Comments | Responsible Party | Week | Target By Date | Category
Sales Close / Handoff Meeting |  | Customer PM & GD Regional Manager | Prework | {Date} | Planning
Vendor Requirements, Product Resources, and Pre-implementation Checklists to Internal Facility Stakeholders |  | Customer PM | Prework | {Date} | Planning
Sign into GD’s Implementation Basecamp Project; ensure all relevant team members have access |  | Customer PM & Customer Team | Prework | {Date} | Planning
Coordinate Internal Technical Stakeholders for project |  | Customer PM | Prework | {Date} | Planning
Schedule Project Kickoff Meeting |  | Customer PM & General Devices | Prework | {Date} | Planning
Milestone: Project Kickoff Call |  | Customer PM & General Devices | Week 1 |  | Planning
Facility procures small format PC |  | Customer PM | Week 2 | {Date} | Hardware
Sent photos of current radio configuration to GD |  | Customer PM | Week 2 | {Date} | Hardware
Determine Equipment Needs; Workstation Needs, PCs, Monitors, Etc |  | Customer PM & General Devices | Week 2 | {Date} | Hardware
Conduct Space Planning and Determine Technical Needs: Telecom Lines, Network Drops, etc. |  | Customer PM, ED Lead, General Devices | Week 2 | {Date} | Hardware
DNS names created |  | Customer PM | Week 3 | {Date} | Server Setup
Remote Access Established Via GD SecureLink Instance |  | Customer PM | Week 3 | {Date} | Server Setup
Server built to specifications | Server spec can be found here - https://general-devices.com/files/documents/CAREpoint/User-Documents/CP3_Requirements.pdf | Customer PM/IT | Week 3 | {Date} | Server Setup
SSL certificate added |  | Customer PM | Week 3 | {Date} | Server Setup
PC imaged for facility |  | Customer PM | Week 3 | {Date} | Hardware
Server configuration confirmed by GD |  | General Devices | Week 4 | {Date} | Server Setup
CAREpoint 3 Hardware Delivered |  | Customer PM | Week 5 | {Date} | Hardware
CAREpoint 3 Hardware Shipped |  | General Devices | Week 4 | {Date} | Hardware
CAREpoint 3 Software install completed |  | General Devices | Week 5 | {Date} | Server Setup
Milestone: CAREpoint 3 Software Installation Complete |  | General Devices | Week 5 |  | Server Setup
Schedule network test |  | General Devices | Week 5 | {Date} | Testing/Training
Facility PC installed on monitor mount | Needs to happen prior to network testing | Customer PM | Week 5 | {Date} | Hardware
Customer provides DSX User Access list |  | Customer PM | Week 6 | {Date} | Testing/Training
Verify Radio Vendor availability for installation |  | General Devices & Customer PM | Week 6 | {Date} | Testing/Training
Schedule Network Testing |  | General Devices & Customer PM | Week 6 | {Date} | Testing/Training
Complete Network test |  | General Devices & Customer PM | Week 7 | {Date} | Testing/Training
Milestone: Network Test Complete |  | General Devices & Customer PM | Week 7 |  | Testing/Training
GD Create DSX User Accounts |  | General Devices | Week 8 | {Date} | Testing/Training
DSX Training for End Users |  | General Devices & Customer PM | Week 8 | {Date} | Testing/Training
Provide GD with EMS Agencies for CAREpoint Intake Form |  | Customer PM | Week 8 | {Date} | Software configuration
Installation/Go live date confirmed |  | General Devices | Week 8 | {Date} | Go Live & Support
Training Scheduled for staff/super users |  | General Devices & Customer PM | Week 8 | {Date} | Testing/Training
Training Completed |  | General Devices | Week 10 | {Date} | Testing/Training
Installation Completed / Go Live |  | General Devices & Customer PM | Week 12 | {Date} | Go Live & Support
Milestone: Go Live Achieved |  | General Devices & Customer PM | Week 12 |  | Go Live & Support
Post go-live: Facility provides setup images |  | Customer PM | Week 12 | {Date} | Go Live & Support
Client Success check-in (1 day, 1 week post go-live) |  | General Devices | Week 12 + | {Date} | Go Live & Support

## e-bridge
Note: Each additional service line (workflow such as STEMI, Stroke, Trauma, Sepsis, etc.) adds approximately 4 weeks to the implementation timeline, following the same cycle outlined below.
{Customer Name} e-Bridge Connect Implementation Project Plan
|  | e-Bridge {version} Go-Live | {Date}
|  | Estimated Project Completion: | {Date}
Customer Name:
Item | Comments | Responsible Party | Week | Target By Date
Sales Close/Handoff Meeting |  | Regional Manager/Customer PM | Prework | {Date}
Security and Technical Assessments Completed |  | Customer PM & Security Team | Prework | {Date}
Confirm all parties needed (IT, ED, Security, Service Line Teams) |  | Customer PM & GD | Prework | {Date}
Sign into GD's Implementation Basecamp Project; Ensure all relevant team members have access |  | Customer PM | Prework | {Date}
Schedule project kickoff meeting |  | General Devices/Customer PM | Prework | {Date}
Confirm all parties needed (IT, ED, Security, Service Line Teams) |  | Customer PM & GD | Prework | {Date}
(Milestone) Kickoff Call |  | General Devices | Prework
Identify initial use cases, activations |  | Customer PM & GD | Week 1 | {Date}
Confirm Implementation Scope |  | Customer PM & GD | Week 1
Security and Technical Assessments Completed |  | Customer PM & GD | Prework | {Date}
Begin Template Design (General Intake Form approach) |  | Customer PM & GD | Week 2 | {Date}
Events/Activations and Roles Identified |  | Customer PM | Week 3 | {Date}
Supply GD with a list of users & roles |  | Customer PM | Week 3 | {Date}
List of Devices and PCs prepared and supplied to GD |  | Customer PM | Week 3 | {Date}
Remote Access established via SecureLink Nexus | If CAREpoint 3 is implemented this can marked completed | Customer PM | Week 3 | {Date}
DSX Server built to specifications | If CAREpoint 3 is implemented this can marked completed | General Devices | Week 3 | {Date}
Begin Account Creation & Hardware Review (PC/Monitors) |  | Customer PM & GD | Week 3 | {Date}
Templates Built |  | General Devices | Week 4 | {Date}
Template Demo Completed |  | General Devices | Week 4 | {Date}
Review & Approve Templates |  | Customer PM | Week 4
Users Created |  | General Devices | Week 5 | {Date}
Login Credentials Provided |  | General Devices | Week 5
Software Installed on Devices |  | Customer PM | Week 5
Confirm PC Configurations (no sleep, no auto logoff, no AD, etc.) |  | Customer PM | Week 5 | {Date}
Customer Workflow Testing |  | Customer PM & GD | Week 5-6 | {Date}
Customer Approves Workflow |  | Customer PM | Week 5
List of Users for DSX Access provided to GD |  | Customer PM | Week 5 | {Date}
End User Training |  | Customer PM & GD | Week 6 | {Date}
Go Live! |  | Customer PM & GD | Week 6 | {Date}
GD provides DSX users |  | GD | Week 6 | {Date}
DSX Training |  | Customer PM & General Devices | Week 6 | {Date}
Service Line Expansion (+4 Weeks per additional workflow)
Service Line Template Design & Build | Repeat for STEMI, Stroke, Trauma, Sepsis, etc. | Customer PM & GD | Week 1 | {Date}
Template Demo & Review |  | General Devices | Week 2 | {Date}
Template Approval |  | Customer PM | Week 2
User List, Devices & PCs Updated |  | Customer PM | Week 2 | {Date}
Accounts Created & Updated |  | Customer PM & GD | Week 2 | {Date}
Customer Workflow Testing |  | Customer PM & GD | Week 3 | {Date}
End User Training | Typically runs concurrent to testing | Customer PM & GD | Week 3 | {Date}
Workflow Approval |  | Customer PM | Week 3
Go Live! for Service Line |  | Customer PM & GD | Week 4 | {Date}