## e-Bridge Connect Plan
Note: Each additional service line (workflow such as STEMI, Stroke, Trauma, Sepsis, etc.) adds approximately 4 weeks to the implementation timeline, following the same cycle outlined below.
{Customer Name} e-Bridge Connect Implementation Project Plan
|  | e-Bridge {version} Go-Live |  | {Date}
|  | Estimated Project Completion: |  | {Date}
Customer Name:
Item | Comments | Responsible Party | Week | Target By Date
Sales Close/Handoff Meeting |  | Regional Manager/Customer PM | Prework | {Date}
Security and Technical Assessments Completed |  | Customer PM & Security Team | Prework | {Date}
Confirm all parties needed (IT, ED, Security, Service Line Teams) |  | Customer PM & GD | Prework | {Date}
Sign into GD's Implementation Basecamp Project; Ensure all relevant team members have access |  | Customer PM | Prework | {Date}
Schedule project kickoff meeting |  | General Devices/Customer PM | Prework | {Date}
Confirm all parties needed (IT, ED, Security, Service Line Teams) |  | Customer PM & GD | Prework | {Date}
(Milestone) Kickoff Call |  | General Devices | Prework
Identify initial use cases, activations |  | Customer PM & GD | Week 1 | {Date}
Confirm Implementation Scope |  | Customer PM & GD | Week 1
Security and Technical Assessments Completed |  | Customer PM & GD | Prework | {Date}
Begin Template Design (General Intake Form approach) |  | Customer PM & GD | Week 2 | {Date}
Events/Activations and Roles Identified |  | Customer PM | Week 3 | {Date}
Supply GD with a list of users & roles |  | Customer PM | Week 3 | {Date}
List of Devices and PCs prepared and supplied to GD |  | Customer PM | Week 3 | {Date}
Remote Access established via SecureLink Nexus | If CAREpoint 3 is implemented this can marked completed | Customer PM | Week 3 | {Date}
DSX Server built to specifications | If CAREpoint 3 is implemented this can marked completed | General Devices | Week 3 | {Date}
Begin Account Creation & Hardware Review (PC/Monitors) |  | Customer PM & GD | Week 3 | {Date}
Templates Built |  | General Devices | Week 4 | {Date}
Template Demo Completed |  | General Devices | Week 4 | {Date}
Review & Approve Templates |  | Customer PM | Week 4
Users Created |  | General Devices | Week 5 | {Date}
Login Credentials Provided |  | General Devices | Week 5
Software Installed on Devices |  | Customer PM | Week 5
Confirm PC Configurations (no sleep, no auto logoff, no AD, etc.) |  | Customer PM | Week 5 | {Date}
Customer Workflow Testing |  | Customer PM & GD | Week 5-6 | {Date}
Customer Approves Workflow |  | Customer PM | Week 5
List of Users for DSX Access provided to GD |  | Customer PM | Week 5 | {Date}
End User Training |  | Customer PM & GD | Week 6 | {Date}
Go Live! |  | Customer PM & GD | Week 6 | {Date}
GD provides DSX users |  | GD | Week 6 | {Date}
DSX Training |  | Customer PM & General Devices | Week 6 | {Date}
Service Line Expansion (+4 Weeks per additional workflow)
Service Line Template Design & Build | Repeat for STEMI, Stroke, Trauma, Sepsis, etc. | Customer PM & GD | Week 1 | {Date}
Template Demo & Review |  | General Devices | Week 2 | {Date}
Template Approval |  | Customer PM | Week 2
User List, Devices & PCs Updated |  | Customer PM | Week 2 | {Date}
Accounts Created & Updated |  | Customer PM & GD | Week 2 | {Date}
Customer Workflow Testing |  | Customer PM & GD | Week 3 | {Date}
End User Training | Typically runs concurrent to testing | Customer PM & GD | Week 3 | {Date}
Workflow Approval |  | Customer PM | Week 3
Go Live! for Service Line |  | Customer PM & GD | Week 4 | {Date}